Kensington Public Library Strategic Plan Implementation Timetable

Goal: Increase Community Awareness

| Objectives by Year | 17 | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| By Quarter | 4th | 1st | 2nd | 3rd | 4th | 1st | 2nd | 3rd | 4th | 1st | 2nd | 3rd | 4th |
| Better promote the library to residents as a source to access information and Technological services |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Identify promotional sites in town for library messages? Like bulletin boards? |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Initiate bi-annual letters to the Social Trustees’ “25ers” list |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Create visual identity/symbol/logo |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Recruit KES/KPL Ambassadors to meet monthly with KPL librarians and report to KES students |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Create more consistent and frequent messaging through media outlets |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Survey NH library websites for design and messaging ideas |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Begin Planning for 125th anniversary of the library |  |  |  |  |  |  |  |  |  |  |  |  |  |

Goal: Expand Programs and Services

| Objectives by Year | ‘17 | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| By Quarter | 4th | 1st | 2nd | 3rd | 4th | 1st | 2nd | 3rd | 4th | 1st | 2nd | 3rd | 4th |
| Survey other libraries for program ideas and expand and develop programs for all ages |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Offer classes on accessing available databases such as Heritage, EBSCO and Ancestry |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Provide more hands-on materials for children |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Reorganize interior spaces to increase opportunities for collaborative work |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Add laptops to allow mobility for computer work |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Assess future technology needs through survey of patrons and innovation research |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Enlist KPL Computer Ambassadors to assist with instructional services for patrons |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Assess availability of additional databases for patron use to be used remotely |  |  |  |  |  |  |  |  |  |  |  |  |  |

Investigate new Integrated Library System (online circulation and catalog) for improved patron experience in accessing Library’s holdings.

Goal: Increase Functionality of Space

| Objectives by Year | ‘17 | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| By Quarter | 4th | 1st | 2nd | 3rd | 4th | 1st | 2nd | 3rd | 4th | 1st | 2nd | 3rd | 4th |
| Establish Inventory of space needs growing from programmatic needs |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Engage consultant/architect to evaluate building space utilization |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Undertake comprehensive review of Sawyer Room holdings, including continued storage Of Kensington Historical Society materials |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Determine hours of operation to maximize patron usage |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Establish matrix of hours that would meet program needs described above |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Design and create an outdoor reading/garden area outside children’s room in back |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Coordinate new garden/reading area with other landscape renewal |  |  |  |  |  |  |  |  |  |  |  |  |  |

Goal: Ensure Financial Support

| Objectives by Year | ‘17 | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| By Quarter | 4th | 1st | 2nd | 3rd | 4th | 1st | 2nd | 3rd | 4th | 1st | 2nd | 3rd | 4th |
| Establish a program of “Library Sponsors”—town/area businesses and organizations which would support Library programs and assist with library needs |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Research grant opportunities to add to the collection, improve technology and provide funding for increased hours of operation and capital improvements |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Review funding initiatives undertaken by other NH libraries |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Expand the number of contributors to the “25ers” club |  |  |  |  |  |  |  |  |  |  |  |  |  |